## Slide 1
B&H
B2B HUB MODERNIZATION
Phase 1
Project Brief
UX · Project Management · Architecture
Weblogic → Aperture
Segment → Sign-Up Centered
JSON Content Layer
April 2026

## Slide 2
CONTEXT
Two Simultaneous Transformations
Phase 1 is not an incremental update — it's a coordinated platform and UX reset.
B&H Photo Video Pro Audio · B2B Hub Modernization · Phase 1
CONFIDENTIAL
PLATFORM
Weblogic → Aperture
The B2B Hub is migrating off Weblogic onto Aperture. Phase 1 deliverables are built on Aperture from day one — not patched onto the legacy stack.
Weblogic's hard-coded architecture is a root cause of content drift and operational bottlenecks. Aperture removes those constraints and makes the JSON content layer viable.
UX MODEL
Segment-Centered → Sign-Up Centered
The hub was built as a browsing model — visitors navigate segments before finding a sign-up path. Phase 1 makes sign-up the primary CTA on entry.
A qualification-first funnel collects org type, state, and contact info upfront. Cooperative contract options are revealed after qualification — reducing misrouting and support overhead.

## Slide 3
PROBLEM
Why the Current Hub Isn't Working
B&H Photo Video Pro Audio · B2B Hub Modernization · Phase 1
CONFIDENTIAL
Content Is Locked in Code
Every headline, logo, and contract listing is hard-coded. A single copy change requires a Jira ticket, dev time, QA, and a deployment cycle. Even a logo update can take months.
Sign-Up Is Buried
Users must browse segments and sub-pages before reaching a registration option. No contact info is captured upfront, creating misrouting and wasted rep time.
Routing Logic Is Hard-Coded
State-to-contract-to-portal routing is embedded in the codebase. Adding a new state, contract, or portal association requires a developer. No self-service path exists.
Weblogic Constrains Everything
The legacy platform makes CMS extensibility impractical. Every architectural improvement is bottlenecked by platform limitations that Aperture is designed to remove.

## Slide 4
PHASE 1 SCOPE
Four Strategic Pivots
B&H Photo Video Pro Audio · B2B Hub Modernization · Phase 1
CONFIDENTIAL
01
Weblogic → Aperture
All Phase 1 deliverables built on Aperture. No new work on Weblogic. Platform migration and hub modernization are coordinated, not sequential.
02
Segment Browsing → Sign-Up First
Sign-up is the hero CTA. Qualification-first funnel collects org type, state, and contact info before surfacing cooperative contracts or portal options.
03
Hard-Coded → JSON Content Layer
All hub, segment, and contract page content driven by JSON config. CMS admin panel enables the B2B team to publish changes without developer involvement.
04
Fixed Routing → JSON-Managed
Contract × segment × state routing logic moved from hard-coded to JSON-configurable. New associations added via CMS — no code change required.

## Slide 5
UX TRANSFORMATION
From Segment Browsing to Qualification-First Sign-Up
B&H Photo Video Pro Audio · B2B Hub Modernization · Phase 1
CONFIDENTIAL
BEFORE · Weblogic · Segment-Centered
1. Hub landing page → browse 12 segment tiles
2. Click into segment page → read content
3. Find sign-up link → start registration
4. D&B verification (high failure rate, poor errors)
5. Routing to portal — often wrong segment
AFTER · Aperture · Sign-Up Centered
1. Hub landing → Sign-Up CTA is hero-level
2. Step 1: Org type + State (deduces segment)
3. Step 2: Contact info + optional B2C account link
4. Step 3: Review → cooperative contracts revealed
5. Account created → routed to correct portal

## Slide 6
JSON CONTENT LAYER
Replacing Hard-Code with Configurable JSON
Every content field and routing rule becomes editable — no dev ticket required.
B&H Photo Video Pro Audio · B2B Hub Modernization · Phase 1
CONFIDENTIAL
Hub & Segment Pages
→ Hero headline + subheadline
→ Body copy + benefit bullets
→ CTA labels + routing URLs
→ FAQ items + SEO meta fields
Contract Pages
→ Contract name, logo, blurb
→ Contract number + eligibility states
→ Primary + secondary CTA URLs
→ Add/update without code change
Contract × Segment × State Routing
→ State → cooperative contract mapping
→ Segment → portal routing rules
→ New associations via CMS admin
→ No code deploy required
CMS Admin Panel (React prototype → production): three-group sidebar · draft/publish workflow · audit log · role-based access · Ariel Goldman publish rights

## Slide 7
CONSTRAINTS
Constraints the Team Needs to Navigate
B&H Photo Video Pro Audio · B2B Hub Modernization · Phase 1
CONFIDENTIAL
Manny Approval Gate
Customer-facing changes require Manny's sign-off before going live. Manny is unavailable until approximately May 2026. Phase 1 build can proceed; launch is gated.
Aperture Migration Sequencing
Phase 1 must be built on Aperture. Any work delivered on Weblogic first creates porting liability. Migration timeline alignment is open question #1 for the architect session.
PMO 5000 — Existing-Customer Routing
Routing logic for existing B2B accounts is architecturally unresolved. Current lean: apply new routing to new sign-ups only; leave existing accounts unchanged. Not formally closed.
BDBTools Preserved Read-Only in Phase 1
The ~350-parameter portal management tool (Sam Herman) is read-only in Phase 1. The JSON layer wraps above it. Full parameter migration is Phase 2 scope.

## Slide 8
TIMELINE
Path to Phase 1 Launch
B&H Photo Video Pro Audio · B2B Hub Modernization · Phase 1
CONFIDENTIAL
Now
Feasibility Discussion
Architects confirm Aperture readiness, migration sequencing, and JSON routing model. State/contract routing ownership decided.
Apr–May
UX Sizing & Alignment
Meet with UX leadership and designers to size the sign-up flow, segment pages, and CMS admin panel. Effort estimate produced.
May
Prototype & Requirements Refinement
Prototype iterated with stakeholder feedback. Requirements locked with Ariel Goldman, Brendan Bagley, and B2B team.
May–Jun
UX Design Mockups
Jay Linder produces high-fidelity designs for sign-up flow, hub landing, segment pages, contract pages, and CMS admin panel.
Jun
Stakeholder Approval
Ariel Goldman and Manny sign off on customer-facing designs. Manny availability (~May 2026) gates this milestone.
Jun–Jul
Handoff to Project Management
Approved designs and requirements handed to PM for sprint planning, ticket grooming, and developer assignment.

## Slide 9
OPEN QUESTIONS
Questions We Need to Answer Together
B&H Photo Video Pro Audio · B2B Hub Modernization · Phase 1
CONFIDENTIAL
Architecture
Migration sequencing: which Phase 1 components land on Aperture first vs. Weblogic? Who owns the migration timeline and how does it gate our build start?
Architecture
State/contract routing location: does routing config live in the new JSON/CMS tool, or remain in BDBTools? Two options need to be compared before we finalize the data model.
Architecture
CMS authentication: leverage existing B&H admin infrastructure or a standalone system?
UX
Effort sizing: what is the design effort for the qualification-first sign-up flow, hub landing redesign, segment pages, and CMS admin panel?
PM
Sprint planning readiness: once UX designs and requirements are approved, what is the lead time to first sprint? What grooming format does the team prefer?

## Slide 10
THE ASK
What We Need
From This Room
Architecture
Confirm Aperture migration sequencing for Phase 1. Align on JSON routing model and CMS auth approach at the April 14 architect session.
UX Leadership
Schedule sizing session with Jay Linder and design team. Confirm resource availability for sign-up flow, hub landing, and CMS admin panel designs.
Project Management
Confirm grooming and sprint planning format. Align on handoff readiness criteria so PM can begin planning as soon as designs are approved.
B&H Photo Video Pro Audio · B2B Hub Modernization · Phase 1
CONFIDENTIAL